## Sheet1
No. | Product Deliverables | Task | Pham Hong Sang | Huynh Thanh Viet | Tran Tan Len | Ha Chi Danh | Unit | Size
1 | Report 1 - Introduction | Project Information | O
|  | Introduction | O
|  | Problem Definition | O
|  | Proposed Solution | O
|  | Functional Requirement | O
|  | Role and Responsibility | O
2 | Report 2- Software Project Management Plan | Problem Definition | O
|  | Project Organization | O
|  | Project Management Plan | O
|  | Coding Convention | O
| Report 3- Software Requirement Specification | User Requirement Specification
3 |  | Guest Requirement
Search Product
|  | Add to cart |  | O
|  | View Details |  | O
…
Member Requirement
|  | Rating |  |  | O
|  | Recommend |  |  | O
|  | See suggestion |  |  | O
…
Staff Requirement
|  | Train Machine | O
|  | Define or configure the weight of criteria |  | O
|  | Collection the web to mine | O
|  | Manage Parser | O
|  | Import product excel |  |  | O
|  | Import hardware excel |  |  | O
…
|  | Admin Requirement |  | O
System Requirement
|  | Parsing the web to get the useful information | O
|  | Evaluated the inputted product to give suggestion or proposal |  | O
|  | System Requirement Specification | O
|  | Software System Attribute | O
|  | Conceptual Diagram | O
4 | Report 4- Software Design Description | System Architectural Design
|  | Web Architecture | O
|  | Component Diagram |  |  | O
|  | Detailed Description of Components | O
Class Diagram
Class Diagram Explanation
Sequence Diagram
User Interface Design
|  | Guest, Member Design |  |  | O
|  | Admin Design | O
|  | Staff Design |  | O
Database Design
|  | Web Application | O
Algorithms
|  | String Comparison | O
Web Application
5 | Report 5 - Software Implementation and Test Document | Login |  | O |  |  |  | 1
|  | Log out |  | O |  |  |  | 1
|  | Change Password |  | O |  |  |  | 1
|  | Register |  | O |  |  |  | 1
|  | Search Product | O |  |  |  |  | 2
|  | Add Product to Cart |  | O |  |  |  | 2
|  | Compare Product |  | O |  |  |  | 2
|  | Compare detail product |  | O |  |  |  | 3
|  | Feedback |  |  | O |  |  | 1
|  | View Details |  | O |  |  |  | 1
|  | String Comparison | O |  |  |  |  | 5
|  | Rating |  |  | O |  |  | 1
|  | Recommend | O |  |  |  |  | 1
|  | View compare history |  | O |  |  |  | 1
|  | Force Parse Data | O |  |  |  |  | 3
|  | Confirm new hardware |  |  | O |  |  | 2
|  | Confirm new laptop |  |  | O |  |  | 2
|  | Give Suggestion |  | O |  |  |  | 5
|  | Define or configure the weight of criteria |  | O |  |  |  | 2
|  | Write Log |  |  | O |  |  | 1
|  | Notify for User | O |  |  |  |  | 2
|  | Import product from Excel |  |  | O |  |  | 3
|  | Import hardware from Excel |  |  | O |  |  | 3
|  | Train Machine |  |  | O |  |  | 2
|  | Configure System | O |  |  |  |  | 1
|  | Manage Products | O |  |  |  |  | 1
|  | Manage Parser | O |  |  |  |  | 1
|  | Manage Hardware |  |  | O |  |  | 1
|  | Manage Store |  |  | O |  |  | 1
|  | Manage User |  |  | O |  |  | 1
|  | Database Relationship Diagram | O
System Testing Test Case
|  | Guest Test Case |  |  | O
|  | Member Test Case |  | O
|  | Staff Test Case | O
Installation Guide
6 | Report 6 - Software User's Manual | Setting up environment at server side | O
|  | Deployment at server side | O
Setting up environment at client side
|  | Setting up for computer |  | O
User Guide
|  | Guest/Member Guide | O
|  | Admin Guide |  |  | O
|  | Staff Guide | O
Function Point Size
Function Types
| Insert, Delete, Update, Simple Search, Login, Register, simple function or simple query on one table | 1
| Computed functions or joined query | 2
| Complex functions or multiple subquery | 5
| Constraint process and data integrity | 4
| Functions with implementing algorithms | 5
Note on C2: phuong: Each row is a topic in project document. Do not have more than 15 rows in each product deliverable. Content in this template is used for reference only and it is vary in each project
Note on D2: phuong: Only one member in line, who has main repsonsibilty in this task
Note on C12: phuong: Use bold format for tasks which have sub-tasks
Note on C13: phuong: Use Indent for sub-tasks